## Sheet1
| Date | Start (UTC) | End (UTC) | OWLT (sec) | Activity | Time span | Notes
1 | 2020-04-22 | 7:20 | 15:20 | 105-117 | SWA | 8:00 | HIS: Power up. PA-HVPS to 7.75kV to 16kV. MCP to 1.7kV to 2.13kV,. SSD Noise test (if time permits). Power off after the end of the pass.
|  | 7:30 | 11:30 |  | EPD | 4:00
|  | 22:00 | 1:00 |  | WOL
2 | 2020-04-24 | 0:00 | 7:20 | 105-117 |  | 7:20 | Nothing happening before pass this date.
|  | 7:20 | 15:20 |  | SWA | 8:00 | HIS: Power up. PA-HVPS to 14kV before pass then to 22.5kV during pass. Power off just after pass allocated time.
|  | 7:20 | 11:20 |  | EPD | 4:00
|  | 22:00 | 1:00 |  | WOL
3 | 2020-04-28 | 0:00 | 1:00 | 123-139 | WOL
|  | 9:27 | 17:27 |  | SWA | 8:00 | HIS: Power up. PA-HVPS upto 20.5kV before pass then to 26kV during pass. Power off just after the pass.
|  | 9:27 | 17:27 |  | STIX | 8:00
4 | 2020-04-29 | 0:00 | 1:02 | 123-139 | SA Steer
|  | 2:16 | 4:16 |  | EPD |  | Looks like they are off at this point, but not certain.
|  | 9:21 | 17:27 |  | SWA | 8:06 | HIS SSD Noise and Memory tests (if time didn't permit this test on the 22nd) ??? HIS Macro Upload (1 hr), EAS2 Eng Tests (2 hrs)
|  | 9:21 | 17:21 |  | EUI | 8:00 | PAS FDIR Test on and off
|  | 22:00 | 1:00 |  | WOL
5 | 2020-04-30 | 0:00 | 1:00 | 123-139 | WOL
|  | 7:07 | 23:59 |  | EUI |  | EUI non-interactive time
|  | 9:15 | 17:15 |  | SWA | 8:00 | EAS1 Interactive channel investigation.
6 | 2020-05-05 | 14:48 | 19:06 | 146-147 | SWA | 4:18 | Daniel is busy on this day. Should we avoid it? HIS SSD Table Upload (1 hr).
|  | 12:48 | 9:36 |  | SoloHi |  | MTL SWA Suite testing? SoloHi stays on after activity. PAS overnight
7 | 2020-05-06 | 12:42 | 19:00 | 146-147 | SWA | 6:18 | SWA Suite testing. HIS can participate in this. SWA-only pass… seems nothing else is on.
|  | 22:00 | 1:00 |  | WOL
8 | 2020-05-07 | 20:00 | 5:00 | 146-147 | SWA | 9:00 | Out of contact. HIS SSD test ????? Non-interactive time slot… SWA and RPW in parallel. Noise measurement date (check with Andrew)?
RPW & STIX (maybe or maybe not) also on throughout.
9 | 2020-05-08 | 6:22 | 14:22 | 146-147 | SWA | 8:00 | SWA Interactive normal science. Mostly on the MTL.
|  | 6:19 | 14:19 |  | STIX | 8:00
|  | 22:00 | 1:00 |  | WOL
10 | 2020-05-11 | 6:07 | 14:07 | 177-203 | SWA | 8:00 | SWA Interactive normal science. Mostly on the MTL.
|  | 15:07 | 18:07 |  | WOL
11 | 2020-05-20 | 15:00 | 18:00 | 215-248 | SWA IIC | 3:00 | Insitu Inter Instrument test
| 2020-06-01 | 14:13 | 17:13 |  | WOL
12 | 2020-06-02 | 1:00 | 10:17 | 319-362 | SWA EMC | 9:17 | EMC Interference campaign. We must ensure that the WOL happens with SWA off.
13 | 2020-06-15 | [5 empty] | Cruise Phase starts. We are on the MTL.