## Feuil1
Date | Activity |  |  | Ground Segment | SWA ACTIVITY | DOY
2020-05-24 12:10 |  |  |  | no | SWA ON | 145
2020-05-24 14:28 | CEB pass | activity end | GS pass | end | ICC
2020-05-24 18:55 |  |  |  |  | SWA OFF
2020-05-29 14:18 | WOL | activity start | Platform activities | no
2020-05-29 17:18 | WOL | activity end | Platform activities | no |  | 150
2020-05-30 03:38 |  |  |  |  | SWA ON | 151
2020-05-30 04:16 | CEB pass | activity start | GS pass | no | Comet
2020-05-30 04:16 | IU-12 | activity end | EUI | YES
2020-05-30 14:16 | CEB pass | activity end | GS pass | no
2020-05-31 03:39 | HGA steering | activity start | Platform activities | no |  | 152
2020-05-31 04:14 | CEB pass | activity start | GS pass | no
2020-05-31 14:14 | CEB pass | activity end | GS pass | no
2020-05-31 20:30 | SA steering | activity start | Platform activities | no
2020-05-31 20:45 | SA steering | activity end | Platform activities | no
2020-06-01 03:38 | HGA steering | activity start | Platform activities | no |  | 153
2020-06-01 04:13 | CEB pass | activity start | GS pass | no
2020-06-01 13:32 |  |  |  |  | SWA OFF
2020-06-01 14:13 | CEB pass | activity end | GS pass | no
2020-06-01 14:13 | WOL | activity start | Platform activities | no
2020-06-01 17:13 | WOL | activity end | Platform activities | no
2020-06-02 06:47 | IW-6_PAYLOAD EMC | activity start |  | no |  | 154
2020-06-02 23:47 |  |  |  | no | SWA ON EMC | 154
2020-06-03 06:47 |  |  |  | no | SWA OFF | 155
2020-06-02 10:17 | MLG pass | activity start | GS pass | no |  | 155
2020-06-03 10:17 | IW-6_PAYLOAD EMC | activity end | VARIOUS | no
2020-06-02 18:49 | MLG pass | activity end | GS pass | no
2020-06-03 18:48 | WOL | activity start | Platform activities | no
2020-06-03 21:48 | SOL-Rolls | activity start | Platform activities | no
2020-06-03 21:48 | WOL | activity end | Platform activities | no
2020-06-04 10:43 | SOL-Rolls | activity end | Platform activities
2020-06-04 14:00 | SWA-PAS-HIS | activity start | SWA | no | SWA ON UPLOAD | 156
2020-06-05 02:00 | SWA-PAS-HIS | activity end | SWA | no | SWA OFF | 156
2020-06-05 07:15 | CEB pass | activity start | GS pass | no
2020-06-05 16:15 | CEB pass | activity end | GS pass | no
2020-06-14 22:03 | LTP01 |  |  |  | SWA ON