## PAS_Recovery
12th April |  | EAS Recovery
Step | Time UTC | Commanding product to be uplinked | From | Type | Constraints | Timing | Nb. Of CMDs | 1st exec. Time | Last exec. Time | Run Time Length | Comments
1 | 8:30 | AIAF830A | MSTK | CMD SEQ | None | Relative release times | 3 | N/A | N/A | 2 secs | enable S3 forwarding to RT
2 | 8:35 | AIAF830C | MSTK | CMD SEQ | None | Relative release times | 1 | N/A | N/A | 0 sec | enable S6 forwarding to RT
3 | 8:35 | AIAF830E | MSTK | CMD SEQ | None | Relative release times | 4 | N/A | N/A | 3 sess | enable reports forwarding to RT
4 | 8:45 | PDOR_SSWA_EAS_MTL_00003.SOL | FT STACK IMMEDIATE | PDOR | None | Absolute | 4 | 2021.108.23.00.00.500 | 2021.108.23.00.35.500 | N/A | Safe EAS before WOL on DOY 2021.109
5 | 8:50 | PDOR_SSWA_EAS_Recovery1_00003.SOL (INTERACTIVE) | MSTK | PDOR | None | Relative release times | 157 | N/A | N/A | ~4 hrs | CMDs 1 to 5 can be armed and sent in 1 go. Wait for execution of above CMDs and feedback from SWA When GO from SWA received, delta rel. time of 10 hrs of the 1st CMD in the MSTK shall be set to asap and ARM CMDs up to and including the CMD before the next one with a release time of 10 hrs. Wait for execution and feedback from SWA. When SWA provides the GO, repeat the procedure above (up to the next CMD with a release time of 10hrs). Before sending each bunch of CMDs it shall be ensured that there is enough commanding time to release all the CMDs in the bunch. If this is not the case the EAS recovery shall be interrupted. The CMDs remaining in the MSTK shall be saved as a STACK (Name: STACK_SWA_EAS_Recovery_Continue) to continue the next day (14th April)
End of EAS Recovery
14th April |  | EAS Recovery Cont'd
Step | Time | Commanding product to be uplinked | From | Type | Constraints | Timing | Nb. Of CMDs | 1st exec. Time | Last exec. Time | Run Time Length | Comments
1 | 8:30 | AIAF830A | MSTK | CMD SEQ | None | Relative release times | 3 | N/A | N/A | 2 secs | enable S3 forwarding to RT
2 | 8:35 | AIAF830C | MSTK | CMD SEQ | None | Relative release times | 1 | N/A | N/A | 0 sec | enable S6 forwarding to RT
3 | 8:35 | AIAF830E | MSTK | CMD SEQ | None | Relative release times | 4 | N/A | N/A | 3 sess | enable reports forwarding to RT
4 | 8:45 | STACK_SWA_EAS_Recovery_Continue (INTERACTIVE) | MSTK | STACK | Recovery1 run successfully | Relative release times | ? | N/A | N/A | ? | Proceed as on day 12th April (uplinking bunches of commands. Any command with release time = 10 hrs is the 1st command of the next bunch)
5 | ? | PDOR_SSWA_EAS_Recovery2A_00003.SOL | FT STACK IMMEDIATE | PDOR | SWA to decide if 2A OR 2B is uplinked | Absolute | 108 | 2021.106.09.00.00.500 | 2021.106.11.29.00.500 | N/A | To be uplinked at the end of the interactive activities. SWA will decide if PDOR_SSWA_EAS_Recovery2A_00003.SOL OR PDOR_SSWA_EAS_Recovery2B_00003.SOL is uplinked.
|  | PDOR_SSWA_EAS_Recovery2B_00003.SOL | FT STACK IMMEDIATE | PDOR | SWA to decide if 2A OR 2B is uplinked | Absolute | 108 | 2021.106.09.00.00.500 | 2021.106.11.29.00.500
End of EAS Recovery