## Slide 1
ARB #13 SWA Slides
Contents
  SWA-DPU Recovery
  Possible Recovery Timeframe
  SWA-Sensor Recovery
  IORs

## Slide 2: DPU Recovery
PDORs & MDORs
  MDOR table has been uplinked to the SC OBC
  PDORs have been made with relative times and so can be run when it suits the MOC
  2 PDORs: 1 is at MOC, the other is waiting for the MIB update
  The DPU recovery is Non-Interactive
  These PDORs have all been converted to a MOC stack already
When ??
  As suggested by MOC, this is planned to recover on 31st March

## Slide 3: SWA Recovery Timetable

## Slide 4: Sensor Recovery Status
HIS
  Recovery PDORs have been delivered to MOC
  Absolute timing
  Will operate completely Non-Interactively from the MTL
  Starts at ~01:00 on 1st April
  Ends at ~23:00 on 4th April
  HIS NM will produce ~61 MiB/day of S15 science data in a 24 period
  -> ~235 MiB in total for the ~4 recovery days
  HIS will be left in a safe LV, Non-Ops state for the WOL on Monday 5th
  Then HIS will remain in that safe state

## Slide 5: Sensor Recovery Status
PAS
  Recovery PDORs have been delivered to MOC
  These have relative timings and are interactive
  There are 10 hour gaps between 4 batches of commands
  Planned to be run between ~14:20 and 19:00 on the 8th
  And between ~14:20 and 19:00 on the 9th
  PAS NM produces ~7.5 MiB of S15 science data per day (assuming compression ratio = 20)
  On day 1, PAS will produce ~0.15 MiB of S15 science data over the interactive slots
  On day 2, PAS will produce ~0.93 MiB of S15 science data over the interactive slots
  PAS will be powered off at the end of the activity via an MTL PDOR

## Slide 6: Sensor Recovery Status
EAS
  EAS will be powered on to heat at the start of the PAS recovery
  It will only produce HK
  Plan to recover EAS the week after PAS (starting the 12th)
  Recovery PDORs are being prepared by MSSL
  EAS requires real time science data to monitor the safe ramp up of it’s HVs after 4 months down time
  Recovery will need to be interactive over 7 steps
  In High Cadence (less demanding on the DPU)
    ~79 MiB of S15 science data during the Int’ slots
    ~270 MiB for 24 hrs
  In Low Cadence (more demanding on the DPU -> moments)
    ~8 MiB of S15 science data during the Int’ slots
    ~27 MiB for 24 hrs
  These values can be reduced by stopping science while waiting for ‘real time’ monitor data

## Slide 7: IORs
STP 143 (12-18 Apr) delivered yesterday
This reacts to WOL & SA rot. Ignore planned TFF and Do Not enter SAFE
Any power OFF around MAINT (Any) have been removed
There is no sensor commanding in these IORs
STP 144 (19-25 Apr) planned to be the same
STP 145 (26-02 May) currently planning this to be the same
STP 146 (03-09 May) hopefully full sensor ops by IOR